Scope of Work

Team Members: Lucas Lee

Date Originally Submitted for Review: 2/27/2026

Date Updated and Resubmitted: 5/8/2026

Submitted to: CIVE 202 Course Instructors

Project Goals:

The goal of this project is to write a script in Python to automate calculations for a W-shaped steel tension member. The script will then be tested with three different scenarios, and a report will be written to be presented to the client. The client has specifically requested that the report include an explanation of the functions, inputs, and outputs used to automate the calculations as well as a discussion of how the calculations were automated. This should also include an explanation of how to use the functions for future employees of the client.

Project Tasks:

Task 1 – Create logic for calculations

AISC Steel Construction Manual, Parts 3 and 5, and AISC Specification for Structural Steel Buildings, Chapter D, will be thoroughly consulted to determine the proper logic and workflow for performing calculations for steel W-sections in tension. Steel Construction Manual includes guidelines and equations for calculations. The equation to determine limit state from this manual will be automated.

Task 2 – Implement logic as a Python script

Functions will be written to perform the limit state function in Python. A function will also be written to search Table 5-1 from the provided manual to find a suitable beam. This will require importing Table 5-1 and cleaning and manipulating it using the Pandas package in order to use it with the function. The functions will then be tested with three different scenarios. The results of each test will then be plotted on a graph using a Python library such as Matplotlib and Seaborn. The type of graph will be determined at a later date. An annotated code document will be included with the final report. The code itself will be housed in a GitHub repository

Task 3 – Produce a report

A report will be written explaining the functions used for calculations as well as the inputs and outputs used in each function. It will also discuss the process of automating the calculations, and it will explain how to use the functions for future Kiewit employees. The report will also include discussion of the results of each of the three scenarios with the relevant graphs from each scenario.

Project Deliverables:

| Deliverable: | Due to Client By: |
| --- | --- |
| Draft Gantt Chart | 3/6/26 |
| Flow Diagram | 3/13/26 |
| Draft Reproducible Methods | 3/27/26 |
| Initial Results | 4/3/26 |
| Technical Executive Summary | 5/8/26 |
| Non-Technical Executive Summary | 5/8/26 |
| Final Report | 5/8/26 |
| GitHub Repository | 5/8/26 |
| Final Timesheet | 5/8/26 |

Note: The Gantt Chart and Timesheet are not included in the tasks. These are simple, standard methods of keeping track of project progress and cost.

The Executive Summaries and the Reproducible Methods are also not included in the tasks because it has not yet been made clear what these deliverables will require.