## cat
Project 5
CIVE 202 |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Lucas Lee
Project start date: | 2026-05-08 |  |  |  |  | May | [27 empty] | June
Scrolling increment: | 0 | time axis 2026-05-08 to 2026-07-02
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2026-05-08 to 2026-07-02
Weekly Deliverables
Flow Diagram | Low Risk | Lucas | 100% | 2026-03-07 | 7
Draft Reproducible Methods | Low Risk | Lucas | 100% | 2026-03-14 | 14
Initial Results | Low Risk | Lucas | 100% | 2026-03-28 | 7
Files for Peer Review | Low Risk | Lucas | 100% | 2026-04-04 | 14
Programing Tasks
Develop Logic | Low Risk | Lucas | 100% | 2026-03-07 | 21
Implement Logic in Python | Low Risk | Lucas | 100% | 2026-03-14 | 21
Project Tasks
Non-Technical Executive Summary | Low Risk | Lucas | 0% | 2026-04-18 | 21
Technical Executive Summary | Low Risk | Lucas | 0% | 2026-04-18 | 21
Fianl Report | Low Risk | Lucas | 100% | 2026-04-18 | 21
To add more data, Insert new rows ABOVE this one